**Key deliverables**

● User Interface

We have design user interface according to the software requirements from the project perspective. We use php technology to develop website as front end and back development is developed in the next phase.

Technology used:

1. Html

2. Css

3. Js

4. Bootstrap5

● Backend Development

We develop systems according to Functional and Non-Functional and use static design of the first phase.

Technology used:

1. PHP

2. MySql

● Setup test system

Once software and hardware are designed, we will set up a test environment in localhost. To debug and fix bugs if they exist.

● Setup live system

After a successful attempt of a system test we compile the production version.

● Data migration

To migrate projects from one system to another system we export sql files and zip compiled production files.

● User Training

We develop systems. Now it's time to write user documentation to guide users on how to use the system.

**Project milestones and its timeframes**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task Name | Duration | Start | Finish | Milestones | |
| **LANDMARK COMPUTERS** | **26 days** | **Wed 27/07/22** | **Sun 21/08/22** |  | |
| **SYSTEM REQUIREMENTS** | **4 days** | **Wed 27/07/22** | **Sat 30/07/22** |  | |
| * FUNCTIONAL REQUIREMENTS * NON-FUNCTIONAL REQUIREMENTS | **4 days** | **Wed 27/07/22** | **Sat 30/07/22** |  | |
| **SYSTEM ARCHITECTURE** | **8 days** | **Sun 31/07/22** | **Sun 31/07/22** | |  | |
| * SOFTWARE DESIGN | **4 days** | **Sun 31/07/22** | **Wed 3/08/22** |  | |
| * HARDWARE DESIGN | **4 days** | **Thu 4/08/22** | **Sun 31/07/22** |  | |
| **SYSTEM DESIGN** | **7 days** | **Mon 8/08/22** | **Sun 14/08/22** |  | |
| * USER INTERFACE DESIGN | **4 days** | **Mon 8/08/22** | **Thu 11/08/22** |  | |
| * BACKEND DEVELOPMENT | **3 days** | **Fri 12/08/22** | **Sun 14/08/22** |  | |
| **SETUP TEST SYSTEM** | **2 days** | **Mon 15/08/22** | **Tue 16/08/22** |  | |
| **SETUP LIVE SYSTEM** | **1 days** | **Wed 17/08/22** | **Wed 17/08/22** |  | |
| **DATA MIGRATION** | **1 days** | **Thu 18/08/22** | **Thu 18/08/22** |  | |
| **USER TRAINING** | **1 days** | **Fri 19/08/22** | **Fri 19/08/22** |  | |
| **Final punch out** | **1 days** | **Sat 20/08/22** | **Sat 20/08/22** |  | |
| **Project completion** | **1 days** | **Sun 21/08/22** | **Sun 21/08/22** |  | |